## Feuil1
client | FRD Nr | Items | Ref | lenght in M | Qty | dead line | expected delivery | STATUS | Comment
CTBTO | 2016-1550 FRD0003 | MB3a |  |  | 10 | 2017-05-19 |  | delivered
|  | Reponse of acoustical calibration | METRO-SENS_AC |  | 10
|  | Measurement of sensor self noice | METRO-SENS_SN |  | 10
|  | Reponse by electrical calibration | METRO-SENS_EC |  | 10
|  | Mb3a Power cable | PR000187-A | 3 | 10
|  | Signal Cable | PR000161-A | 3 | 10
Printed MB3a User Guide
|  | Screw pack Plastic tube with foam | PR000169 |  | 10
CTBTO | 2016-1550 FRD0003 | MB3a |  |  | 10 | 2017-06-21 | week 39 | METROLOGY IN PROGRESS | Delay due to the lack of availabilities of the CEA accoustic test bench. The Seismo Wave acoustic test bench has been verified by the CEA on week 37
|  | Reponse of acoustical calibration | METRO-SENS_AC |  | 10 |  | week 39 | METROLOGY IN PROGRESS
|  | Measurement of sensor self noice | METRO-SENS_SN |  | 10 |  | week 39 | METROLOGY IN PROGRESS
|  | Reponse by electrical calibration | METRO-SENS_EC |  | 10 |  | week 39 | METROLOGY IN PROGRESS
|  | Mb3a Power cable | PR000187-A | 3 | 10 | 42907 | week 39 | READY FOR DELIVERY
|  | Cable signal | PR000161-A | 3 | 10 | 42907 | week 39 | READY FOR DELIVERY
|  | Printed MB3a User Guide |  |  |  |  | week 39 | READY FOR DELIVERY
|  | Screw pack Plastic tube with foam | PR000169 |  | 10 | 42907 | week 39 | READY FOR DELIVERY
CTBTO | 2016-1550 FRD0003 | MB3a |  |  | 10 | 2017-09-21 | week 41 | METROLOGY IN PROGRESS | Delay due to the lack of availabilities of the CEA accoustic test bench. The Seismo Wave acoustic test bench has been verified by the CEA on week 37
|  | Reponse of acoustical calibration | METRO-SENS_AC |  | 10 |  | week 41 | METROLOGY IN PROGRESS
|  | Measurement of sensor self noice | METRO-SENS_SN |  | 10 |  | week 41 | METROLOGY IN PROGRESS
|  | Reponse by electrical calibration | METRO-SENS_EC |  | 10 |  | week 41 | METROLOGY IN PROGRESS
|  | Mb3a Power cable | PR000187-A | 3 | 10 | 42999 | week 41 | READY FOR DELIVERY
|  | Signal Cable | PR000161-A | 3 | 10 | 42999 | week 41 | READY FOR DELIVERY
|  | Printed MB3a User Guide |  |  |  |  | week 41 | READY FOR DELIVERY
|  | Screw pack Plastic tube with foam | PR000169 |  | 10 | 42999 | week 41 | READY FOR DELIVERY
CTBTO | 2016-1550 FRD0004 | MB3a |  |  | 10 | 2017-10-03 | week 45 | MANUFACTURING IN PROGRESS
|  | Reponse of acoustical calibration | METRO-SENS_AC |  | 10 |  | week 45 | SCHEDULED
|  | Measurement of sensor self noice | METRO-SENS_SN |  | 10 |  | week 45 | SCHEDULED
|  | Reponse by electrical calibration | METRO-SENS_EC |  | 10 |  | week 45 | SCHEDULED
|  | Mb3a Power cable | PR000187-A | 3 | 10 |  | week 45 | MANUFACTURING IN PROGRESS
|  | Signal Cable | PR000161-A | 3 | 10 |  | week 45 | MANUFACTURING IN PROGRESS
|  | Magnet wrench | MU000384- |  | 10 |  |  | DELIVERED | on September 4 th
|  | Magnet adjustment cable | PR000082-A |  | 10 |  | week 45 | READY FOR DELIVERY
|  | Pelicase 6 Mb3a with cables | PR000276 |  | 2 |  |  | DELIVERED | on September 4 th
|  | Permanant caps | PR000354 |  | 100 |  |  | DELIVERED | on September 4 th
|  | Printed MB3a User Guide |  |  | 10 |  | week 45 | SCHEDULED
|  | Screw pack Plastic tube with foam | PR000169 |  | 10 |  | week 45 | READY FOR DELIVERY
CTBTO | 2016-1550 FRD0004 | MB3a |  |  | 10 | 2017-11-03 | week 45 | MANUFACTURING IN PROGRESS
|  | Reponse of acoustical calibration | METRO-SENS_AC |  | 10 |  | week 45 | SCHEDULED
|  | Measurement of sensor self noice | METRO-SENS_SN |  | 10 |  | week 45 | SCHEDULED
|  | Reponse by electrical calibration | METRO-SENS_EC |  | 10 |  | week 45 | SCHEDULED
|  | Mb3a Power cable | PR000187-A | 3 | 10 | 42907 | week 45 | MANUFACTURING IN PROGRESS
|  | Signal Cable | PR000161-A | 3 | 10 | 42907 | week 45 | MANUFACTURING IN PROGRESS
|  | Printed MB3a User Guide |  |  |  |  | week 45 | SCHEDULED
|  | Screw pack Plastic tube with foam | PR000169 |  | 10 | 42907 | week 45 | READY FOR DELIVERY
CTBTO | 2016-1550 FRD0004 | MB3a |  |  | 10 | 2017-12-03 | week 49 | MANUFACTURING IN PROGRESS
|  | Reponse of acoustical calibration | METRO-SENS_AC |  | 10 |  | week 49 | SCHEDULED
|  | Measurement of sensor self noice | METRO-SENS_SN |  | 10 |  | week 49 | SCHEDULED
|  | Reponse by electrical calibration | METRO-SENS_EC |  | 10 |  | week 49 | SCHEDULED
|  | Mb3a Power cable | PR000187-A | 3 | 10 | 42999 | week 49 | MANUFACTURING IN PROGRESS
|  | Signal Cable | PR000161-A | 3 | 10 | 42999 | week 49 | MANUFACTURING IN PROGRESS
|  | Printed MB3a User Guide |  |  |  |  | week 49 | SCHEDULED
|  | Screw pack Plastic tube with foam | PR000169 |  | 10 | 42999 | week 49 | READY FOR DELIVERY
CTBTO | 2016-1550 FRD0004 | MB200x to integration box signal cable | PR000404-CBL_3 | 3 | 9 | ASAP |  | Delivered | on September 4 th
|  | MB200x power cable | PR000399-CBL_3 | 3 | 9 |  |  | Delivered | on September 4 th
|  | MB3a signal cable to integration box | PR000403-CBL_3 | 3 | 5 |  |  | Delivered | on September 4 th
|  | Integration box to digitizer signal | PR000487-CBL_3 | 3 | 10 |  | week 45 | PENDING DECISION | confirmation of the type of digitizer and of sensors to be plugged
|  | Pelicase 1520 for integration box | PR000382 |  | 5 | 42999 | week 45 | UNDER DESIGNING
|  | Mb3a integration box 3 connectors | PR000437 |  | 10 | 42999 |  | delivered | on September 4 th
|  | Mb3a integration box 4 connectors | PR000440 |  | 10 | 42999 | week 45 | PENDING DECISION | confirmation of the type of digitizer and of sensors to be plugged
CTBTO | 2016-1550 FRD0005 | Digital MB3d microbarometer |  |  | 15 | 2017-12-10 | week 51 | MANUFACTURING IN PROGRESS | or second week oj january 2018
|  | Reponse of acoustical calibration | METRO-SENS_AC |  | 15 |  | week 51 | SCHEDULED | or second week oj january 2018
|  | Measurement of sensor self noice | METRO-SENS_SN |  | 15 |  | week 51 | SCHEDULED | or second week oj january 2018
|  | Reponse by electrical calibration | METRO-SENS_EC |  | 15 |  | week 51 | SCHEDULED | or second week oj january 2018
|  | Mb3a Power cable | PR000187-A | 3 | 15 | 42999 | week 51 | SCHEDULED
|  | PC/USB cable | PR000188-A | 3 | 15 |  | week 51 | SCHEDULED | for an array of MB3d, a serial communication would be needed. Need to add a serial cable PR000436
|  | GPS PROCOM 2000B TNC antenna |  |  | 15 |  | week 51 | SCHEDULED
|  | GPS Cable | PR000183A | 10 | 15 |  | week 51 | SCHEDULED
|  | Screw pack Plastic tube with foam | PR000169 |  | 15 |  | week 51 | READY FOR DELIVERY
|  | Magnet wrench | MU000384- |  | 2 |  | week 51 | READY FOR DELIVERY
|  | Magnet adjustment cable | PR000082-A |  | 2 |  | week 51 | SCHEDULED | not compliant with the MB3d to adjust the magnet need a PC/ USB cable or a serial cable
|  | Pelicase 6 MB3a or d 1650 | PR000198 |  | 3 |  | week 51 | SCHEDULED
|  | Permanant caps | PR000354 |  | 70 |  | week 51 | MANUFACTURING IN PROGRESS | 31 units on stock ready to be delivered + 23 pending assembly
|  | Mb3a integration box 3 connectors | PR000483 |  | 16 |  | week 51 | PENDING DECISION | confirmation of the type of sensors to be plugged
|  | Integration box to digitizer signal | PR000487-CBL_1 | 1 | 16 | 42999 | week 51 | PENDING DECISION | confirmation of digitizer type
|  | MB200x to integration box signal cable | PR000404-CBL_1 | 1 | 16 | 42999 | week 51 | SCHEDULED
CTBTO | 2016-1550 FRD0006 | MB3a signal cable to integration box | PR000403-CBL_3 | 1 | 3 | ASAP |  | DELIVERED | on September 8th
CTBTO | 2016-1550 FRD0007 | MB3a signal cable to integration box | PR000403-CBL_3 | 3 | 21 |  | week 45 | PENDING DECISION | confirmation of the lenght 3 or 1 meter long and data to be transmitted

## Feuil2
MANUFACTURING IN PROGRESS
UNDER DESIGNING
PENDING DECISION
SCHEDULED
METROLOGY IN PROGRESS
READY FOR DELIVERY
DELIVERED